## Slide 1: Project Time Management: Critical Path Analysis

## Slide 2: Project Time Management Processes
*
UCS 804- Software Project Management
Activity definition: Identifying the specific activities that the project team members and stakeholders must perform to produce the project deliverables.
Activity sequencing: Identifying and documenting the relationships between project activities.
Activity resource estimating: Estimating how many resources a project team should use to perform project activities.
Activity duration estimating: Estimating the number of work periods that are needed to complete individual activities.
Schedule development: Analyzing activity sequences, activity resource estimates, and activity duration estimates to create the project schedule.
Schedule control: Controlling and managing changes to the project schedule.

## Slide 3: Activity Definition
*
UCS 804- Software Project Management
An activity or task is an element of work normally found on the WBS that has an expected duration, a cost, and resource requirements.
Project schedules grow out of the basic documents that initiate a project.
  The project charter includes start and end dates and budget information.
  The scope statement and WBS help define what will be done.
Activity definition involves developing a more detailed WBS and supporting explanations to understand all the work to be done, so you can develop realistic cost and duration estimates.

## Slide 4: Activity Lists and Attributes
*
UCS 804- Software Project Management
An activity list is a tabulation of activities to be included on a project schedule. The list should include:
  The activity name
  An activity identifier or number
  A brief description of the activity
Activity attributes provide more information about each activity, such as predecessors, successors, logical relationships, leads and lags, resource requirements, constraints, imposed dates, and assumptions related to the activity.

## Slide 5: Milestones
*
UCS 804- Software Project Management
A milestone is a significant event that normally has no duration.
It often takes several activities and a lot of work to complete a milestone.
Milestones are useful tools for setting schedule goals and monitoring progress.
Examples include completion and customer sign-off on key documents and completion of specific products.

## Slide 6: Activity Sequencing
*
UCS 804- Software Project Management
Involves reviewing activities and determining dependencies.
A dependency or relationship relates to the sequencing of project activities or tasks.
You must determine dependencies in order to use critical path analysis.

## Slide 7: Critical Path Analysis
*
UCS 804- Software Project Management
Activity
duration
Shower
3
Dry hair
8
Fetch car
7
Iron clothes
12
Dress and make-up
10
Drive to interview
20

## Slide 8: Precedence table
*
UCS 804- Software Project Management
Activity
Immediately preceding activities
duration
A
Shower
-
3
B
Dry hair
A
8
C
Fetch car
-
7
D
Iron clothes
-
12
E
Dress and make-up
B,D
10
F
Drive to interview
C,E
20
The last activities that must be completed before an activity can begin

## Slide 9: Activity on Arc Network
*
UCS 804- Software Project Management
A(3)
D(12)
B(8)
E(10)
C(7)
F(20)
1
5
4
3
2

## Slide 10: Microsoft Project Example
*
UCS 804- Software Project Management

## Slide 11: Microsoft Project Example
*
UCS 804- Software Project Management

## Slide 12: Sample Network Diagram
*
UCS 804- Software Project Management

## Slide 13: Network Diagrams
*
UCS 804- Software Project Management
AOA consists of
    Circles representing Events
      Such as ‘start’ or ‘end’ of a given task
    Lines representing Tasks
      Thing being done ‘Build UI’
    a.k.a. Arrow Diagramming Method (ADM)
AON
    Tasks on Nodes
      Nodes can be circles or rectangles (usually latter)
      Task information written on node
    Arrows are dependencies between tasks
    a.k.a. Precedence Diagramming Method (PDM)

## Slide 14
*
UCS 804- Software Project Management
AOA Project Network for House
3
2
0
1
3
1
1
1
1
2
4
6
7
3
5
Lay foundation
Design house and obtain financing
Order and receive materials
Dummy
Finish work
Select carpet
Select paint
Build house
AON Project Network for House
1
3
2
2
4
3
3
1
5
1
6
1
7
1
Start
Design house and obtain financing
Order and receive materials
Select paint
Select carpet
Lay foundations
Build house
Finish work

## Slide 15
*
UCS 804- Software Project Management
Situations in network diagram
A
B
C
A must finish before either B or C can start
A
B
C
both A and B must finish before C can start
D
C
B
A
both A and B must finish before either of C or D can start
A
C
B
D
Dummy
A must finish before B can start
both A and C must finish before D can start

## Slide 16
*
UCS 804- Software Project Management
Concurrent Activities
2
3
Lay foundation
Order material
(a) Incorrect precedence relationship
(b) Correct precedence relationship
3
4
2
Dummy
Lay
foundation
Order material
1
2
0

## Slide 17: Critical Path Method (CPM)
*
UCS 804- Software Project Management
CPM is a network diagramming technique used to predict total project duration.
A critical path for a project is the series of activities that determines the earliest time by which the project can be completed.
The critical path is the longest path through the network diagram and has the least amount of slack or float.
Slack or float is the amount of time an activity can be delayed without delaying a succeeding activity or the project finish date.

## Slide 18
*
UCS 804- Software Project Management
Forward Pass
Earliest Start Time (ES)
  earliest time an activity can start
  ES = maximum EF of immediate predecessors
Earliest finish time (EF)
  earliest time an activity can finish
  earliest start time plus activity time
    EF= ES + t
Latest Start Time (LS)
  Latest time an activity can start without delaying critical path time
    LS= LF - t
Latest finish time (LF)
  latest time an activity can be completed without delaying critical path time
  LS = minimum LS of immediate predecessors
Backward Pass

## Slide 19: CPM analysis
*
UCS 804- Software Project Management
Draw the CPM network
Analyze the paths through the network
Determine the float for each activity
  Compute the activity’s float
  float = LS - ES = LF - EF
  Float is the maximum amount of time that this activity can be delay in its completion before it becomes a critical activity, i.e., delays completion of the project
Find the critical path is that the sequence of activities and events where there is no “slack” i.e.. Zero slack
  Longest path through a network
Find the project duration is minimum project completion time

## Slide 20: CPM Example:
*
UCS 804- Software Project Management
CPM Network
a, 6
f, 15
b, 8
c, 5
e, 9
d, 13
g, 17
h, 9
i, 6
j, 12

## Slide 21: CPM Example
*
UCS 804- Software Project Management
ES and EF Times
a, 6
f, 15
b, 8
c, 5
e, 9
d, 13
g, 17
h, 9
i, 6
j, 12
0
6
0
8
0
5

## Slide 22: CPM Example
*
UCS 804- Software Project Management
ES and EF Times
a, 6
f, 15
b, 8
c, 5
e, 9
d, 13
g, 17
h, 9
i, 6
j, 12
0
6
0
8
0
5
5
14
8
21
6
23
6
21

## Slide 23: CPM Example
*
UCS 804- Software Project Management
ES and EF Times
a, 6
f, 15
b, 8
c, 5
e, 9
d, 13
g, 17
h, 9
i, 6
j, 12
0
6
0
8
0
5
5
14
8
21
21
33
6
23
21
30
23
29
6
21
Project’s EF = 33

## Slide 24: CPM Example
*
UCS 804- Software Project Management
ES and EF Times
a, 6
f, 15
b, 8
c, 5
e, 9
d, 13
g, 17
h, 9
i, 6
j, 12
0
6
0
8
0
5
5
14
8
21
21
33
6
23
21
30
23
29
6
21
Project’s EF = 33

## Slide 25: CPM Example
*
UCS 804- Software Project Management
LS and LF Times
a, 6
f, 15
b, 8
c, 5
e, 9
d, 13
g, 17
h, 9
i, 6
j, 12
0
6
0
8
0
5
5
14
8
21
21
33
6
23
21
30
23
29
6
21
4
9
0
8
7
12
12
21
21
33
27
33
8
21
10
27
24
33
9
24

## Slide 26: CPM Example
*
UCS 804- Software Project Management
Float or Float
a, 6
f, 15
b, 8
c, 5
e, 9
d, 13
g, 17
h, 9
i, 6
j, 12
0
6
0
8
0
5
5
14
8
21
21
33
6
23
21
30
23
29
6
21
3
9
0
8
7
12
12
21
21
33
27
33
8
21
10
27
24
33
9
24
3
4
3
3
4
0
0
7
7
0

## Slide 27: CPM Example
*
UCS 804- Software Project Management
Critical Path
a, 6
f, 15
b, 8
c, 5
e, 9
d, 13
g, 17
h, 9
i, 6
j, 12
NOTE: All related calculations are shown on Slide 50 onwards.